## WBS
Food Manufacturing Company - Milestones & WBS
Milestone | ID | Task | Owner | Duration (days) | Notes
Analyze Supply Chain Disruptions | 1.1 | Conduct a comprehensive assessment of current sesame seed supply chain disruptions (import restrictions, financial constraints) | Supply Chain Manager | 5 | Assess international and domestic disruptions
| 1.2 | Conduct a comprehensive assessment of the local sesame seed market, identifying potential suppliers and their capabilities | Procurement Team | 4 | Focus on sourcing from local suppliers
| 1.3 | Analyze the impact of supply disruptions on production capacity and product availability | Production Manager | 3 | Include capacity forecasts for tahini production
| 1.4 | Evaluate the quality standards of local sesame seed suppliers to ensure they meet company requirements | Quality Assurance Manager | 4 | Focus on maintaining product quality
| 1.5 | Assess the financial viability of sourcing sesame seeds from local suppliers, including pricing and payment terms | Finance Department | 3 | Include USD and EGP cost considerations
Develop Supplier Relationships & Resilient Sourcing Strategy | 2.1 | Establish initial contact with potential local suppliers and schedule meetings or site visits | Procurement Manager | 5 | Create shortlist of qualified suppliers
| 2.2 | Identify and evaluate potential alternative suppliers of sesame seeds (domestic & international) | Supply Chain Manager | 6 | Explore both international and domestic suppliers
| 2.3 | Explore options for diversifying the supply chain to reduce reliance on a single source | Procurement Manager | 4 | Include both short-term and long-term strategies
| 2.4 | Negotiate favorable terms with suppliers (pricing, delivery schedules, flexible payment terms, long-term contracts) | Procurement & Legal Teams | 7 | Ensure legal review of contracts
| 2.5 | Develop long-term partnerships with reliable suppliers to ensure a consistent supply of sesame seeds | Procurement Team | 10 | Establish formal agreements and service legal agreement
Implement Financial Strategies | 3.1 | Develop a financial plan to address increased costs associated with sesame seed sourcing | Finance Department | 5 | Include currency risk and cost-saving strategies
| 3.2 | Explore options for securing financing to cover upfront payments and operational costs | Finance Director | 5 | Look for local or international financing options
| 3.3 | Implement cost-saving measures to mitigate the financial impact of supply chain disruptions | Operations Manager | 7 | Implement energy efficiency and waste reduction measures
Implement Quality Control & Optimize Production | 4.1 | Develop and implement a rigorous quality control process for incoming sesame seeds | Quality Control Manager | 4 | Ensure adherence to company standards
| 4.2 | Conduct regular inspections and testing to ensure compliance with quality standards | Quality Assurance Team | 7 | Continuous inspections during the production process
| 4.3 | Establish a system for tracking and managing quality issues | Operations Manager | 3 | Focus on addressing issues immediately
| 4.4 | Review and optimize production processes to accommodate the use of local sesame seeds | Production Manager | 6 | Adjust production lines as necessary
| 4.5 | Implement inventory management strategies to ensure optimal stock levels of sesame seeds and finished products | Inventory Manager | 4 | Ensure proper stock levels based on demand
Enhance Customer Relationships | 5.1 | Communicate transparently with customers about challenges and potential product availability issues | Marketing Team | 3 | Use customer communication channels to inform regularly
| 5.2 | Implement strategies to maintain customer loyalty and satisfaction during periods of supply shortages | Business Development Team | 7 | Offer discounts or alternatives
| 5.3 | Develop a long-term customer relationship management plan to build trust and loyalty | CRM Manager | 5 | Focus on loyalty programs and personalized communication
Monitor and Evaluate Performance | 6.1 | Continuously monitor the performance of local suppliers and the quality of sesame seeds | Marketing Team | 3 | Use customer communication channels to inform regularly
| 6.2 | Evaluate the impact of the new sourcing strategy on production costs, product quality, and overall operations | Business Development Team | 7 | Offer discounts or alternatives